## Sheet1
S No. | Indenting Cons.Code | Indenting Consignee | Whether PAC | Indent Ref. | Cons. Code | Consignee | Indent No. | Indent Date Sort | Indent Date | Item No. of Indent | PL/ Item Code | Item Details | Dmd Qty. | Dmd Unit | Consignee Indent Item Value (Rs) | Total Indent Value (Rs) | Min. App. Level | Allocation | Currently with | Status of Indent | Purchase Section | Purchase Dept | Whether Indent Regd? | Purchase Type | Proposal No. | Proposal Date | Whether Proposal Appd | Tender No. | Tender Floating Date | Tender Opening Date | Whether Tender Finalized | Bid by (Firm/ Mfr/ Regd Supplier) | LOA Supplier | PO No. | PO Date | PO Sr. | PL/Item No. | Item Description | PO Cons Rly | PO Cons Code | PO Cons Details | Item Qty. | Item Unit | Item Rate (Rs.) | Item Value (Rs.) | Delivery Date | Qty. Recd. | Qty. Recd. Value(Rs.) | Last MA No. | MA Date | Reason for MA | UWID | Work Order No.
1 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00038 | 2023-08-31 | 31/08/2023 | 1 | 509003090020 | Supply of Moxa NPort S8455I-MM-SC, 4 RS-232/422/485 ports, 5 10/100M Ethernet ports, 2KV Isolation Protection, Input 12-48 VDC, Relay Output 24 VDC Inspection by Consignee with OEM Test report and War.... | 2 | Nos. | 220660 | 220660 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 31/08/23 |  | Stores | Demand has not been registered yet |  |  |  | Proposal has not been approved yet | [16 empty] | 0
2 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00039 | 2023-09-22 | 22/09/2023 | 1 | 539836410071 | Supply of Epoxy Gel Coat with Hardner and Thinner. One set consists of (1) Epoxy Gel- 3Kgs., (2) Epoxy HardnerEH-411-1Kgs. and (3) Epoxy Thinner 221-0.9Kgs. Make-Tuff Bond or Pidilite or Elitecrete o.... | 90 | Set | 240480 | 240480 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 22/09/23 | 90 | Stores | Demand has been registered with File no 90237222 dt.26/09/2023 | Tender - Normal | 90237222 | 18-10-2023 | Proposal Approved with 90237222 dt.18-10-2023 | 90237222 | 02/11/2023 | 15/11/2023 | Tender Finalized | ALLIED GENERAL SALES CORPORATION-CHENNAI | ALLIED GENERAL SALES CORPORATION-CHENNAI | 90237222101919 | 27/11/2023 | 001 | 539836410071 | Supply of Epoxy Gel Coat with Hardner and Thinner. One set consists of (1) Epoxy Gel- 3Kgs., (2) Epoxy HardnerEH-411-1Kgs. and (3) Epoxy Thinner 221-0.9Kgs. Make-Tuff Bond or Pidilite or Elitecrete o.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 90 | Set | 2085 | 187650 | 26-03-2024 | 90 | 187650
3 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00071 | 2023-08-16 | 16/08/2023 | 1 | 561196380137 | Cable PVC insulated, armoured, unscreened, underground Railway signaling, copper cable of size 24C X 1.5 sqmm as per specification no.IRS:S-63/2014 (Rev 4.0) or latest. (Inspection by RDSO) | 5000 | MTR | 1660850 | 1660850 | SAG | 29317304 | SR-CN/MS | Demand Approved & Forwarded to Purchase Unit: - on 16/08/23 |  | Stores | Demand has not been registered yet |  |  |  | Proposal has not been approved yet | [16 empty] | 0 | [7 empty] | 100131211018
4 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00074 | 2023-07-29 | 29/07/2023 | 1 | 561196380137 | Cable PVC insulated, armoured, unscreened, underground Railway signaling, copper cable of size 24C X 1.5 sqmm as per specification no.IRS:S-63/2014 (Rev 4.0) or latest. (Inspection by RDSO) | 1000 | MTR | 332170 | 332170 | Sr. Scale | 29317304 | SR-CN/MS | Demand Approved & Forwarded to Purchase Unit: - on 29/07/23 |  | Stores | Demand has not been registered yet |  |  |  | Proposal has not been approved yet | [16 empty] | 0 | [7 empty] | 100131211018
5 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00075 | 2023-07-29 | 29/07/2023 | 1 | 539887670035 | Cable PVC insulated, armoured, unscreened, underground Railway signaling, copper cable of size 30C X 1.5 sqmm as per specification no.IRS:S-63/2014 (Rev 4.0) or latest. (Inspection by RDSO) | 1000 | MTR | 412410 | 412410 | Sr. Scale | 29317304 | SR-CN/MS | Demand Approved & Forwarded to Purchase Unit: - on 29/07/23 |  | Stores | Demand has not been registered yet |  |  |  | Proposal has not been approved yet | [16 empty] | 0 | [7 empty] | 100131211018
6 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00076 | 2023-07-29 | 29/07/2023 | 1 | 539803142026 | Supply of Cable PVC insulated, armoured, unscreened, underground Railway signaling, copper cable of size 19C X 1.5 sqmm as per specification no.IRS:S-63/2014 (Rev 4.0) or latest. (Inspection by RDSO) | 5000 | MTR | 1325150 | 1325150 | JAG | 29317304 | SR-CN/MS | Demand Approved & Forwarded to Purchase Unit: - on 29/07/23 |  | Stores | Demand has not been registered yet |  |  |  | Proposal has not been approved yet | [16 empty] | 0 | [7 empty] | 100131211018
7 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00077 | 2023-08-16 | 16/08/2023 | 1 | 561196380137 | Cable PVC insulated, armoured, unscreened, underground Railway signaling, copper cable of size 24C X 1.5 sqmm as per specification no.IRS:S-63/2014 (Rev 4.0) or latest. (Inspection by RDSO) | 5000 | MTR | 1660850 | 1660850 | SAG | 29317304 | SR-CN/MS | Demand Approved & Forwarded to Purchase Unit: - on 16/08/23 |  | Stores | Demand has not been registered yet |  |  |  | Proposal has not been approved yet | [16 empty] | 0 | [7 empty] | 100131211018
8 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00078 | 2023-07-29 | 29/07/2023 | 1 | 539887670035 | Cable PVC insulated, armoured, unscreened, underground Railway signaling, copper cable of size 30C X 1.5 sqmm as per specification no.IRS:S-63/2014 (Rev 4.0) or latest. (Inspection by RDSO) | 3000 | MTR | 1237230 | 1237230 | JAG | 29317304 | SR-CN/MS | Demand Approved & Forwarded to Purchase Unit: - on 29/07/23 |  | Stores | Demand has not been registered yet |  |  |  | Proposal has not been approved yet | [16 empty] | 0 | [7 empty] | 100131211018
9 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00079 | 2023-07-29 | 29/07/2023 | 1 | 539803142026 | Supply of Cable PVC insulated, armoured, unscreened, underground Railway signaling, copper cable of size 19C X 1.5 sqmm as per specification no.IRS:S-63/2014 (Rev 4.0) or latest. (Inspection by RDSO) | 500 | MTR | 132515 | 132515 | Sr. Scale | 29317304 | SR-CN/MS | Demand Approved & Forwarded to Purchase Unit: - on 29/07/23 |  | Stores | Demand has not been registered yet |  |  |  | Proposal has not been approved yet | [16 empty] | 0 | [7 empty] | 100131211001
10 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00080 | 2023-07-29 | 29/07/2023 | 1 | 539803142026 | Supply of Cable PVC insulated, armoured, unscreened, underground Railway signaling, copper cable of size 19C X 1.5 sqmm as per specification no.IRS:S-63/2014 (Rev 4.0) or latest. (Inspection by RDSO) | 600 | MTR | 159018 | 159018 | Sr. Scale | 29317304 | SR-CN/MS | Demand Approved & Forwarded to Purchase Unit: - on 29/07/23 |  | Stores | Demand has not been registered yet |  |  |  | Proposal has not been approved yet | [16 empty] | 0 | [7 empty] | 100131211018
11 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00081 | 2023-07-29 | 29/07/2023 | 1 | 561196380137 | Cable PVC insulated, armoured, unscreened, underground Railway signaling, copper cable of size 24C X 1.5 sqmm as per specification no.IRS:S-63/2014 (Rev 4.0) or latest. (Inspection by RDSO) | 500 | MTR | 166085 | 166085 | Sr. Scale | 29317304 | SR-CN/MS | Demand Approved & Forwarded to Purchase Unit: - on 29/07/23 |  | Stores | Demand has not been registered yet |  |  |  | Proposal has not been approved yet | [16 empty] | 0 | [7 empty] | 100131211018
12 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00082 | 2023-07-29 | 29/07/2023 | 1 | 561196380137 | Cable PVC insulated, armoured, unscreened, underground Railway signaling, copper cable of size 24C X 1.5 sqmm as per specification no.IRS:S-63/2014 (Rev 4.0) or latest. (Inspection by RDSO) | 3000 | MTR | 996510 | 996510 | JAG | 29327704 | SR-CN/MS | Demand Approved & Forwarded to Purchase Unit: - on 29/07/23 |  | Stores | Demand has not been registered yet |  |  |  | Proposal has not been approved yet | [16 empty] | 0 | [7 empty] | 100132181003
13 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00083 | 2023-07-29 | 29/07/2023 | 1 | 539887670035 | Cable PVC insulated, armoured, unscreened, underground Railway signaling, copper cable of size 30C X 1.5 sqmm as per specification no.IRS:S-63/2014 (Rev 4.0) or latest. (Inspection by RDSO) | 500 | MTR | 209005 | 209005 | Sr. Scale | 43167304 | SR-CN/MS | Demand Approved & Forwarded to Purchase Unit: - on 29/07/23 |  | Stores | Demand has not been registered yet |  |  |  | Proposal has not been approved yet | [16 empty] | 0 | [7 empty] | 100116211003
14 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00084 | 2023-07-29 | 29/07/2023 | 1 | 539803142026 | Supply of Cable PVC insulated, armoured, unscreened, underground Railway signaling, copper cable of size 19C X 1.5 sqmm as per specification no.IRS:S-63/2014 (Rev 4.0) or latest. (Inspection by RDSO) | 2000 | MTR | 582480 | 582480 | JAG | 43167304 | SR-CN/MS | Demand Approved & Forwarded to Purchase Unit: - on 29/07/23 |  | Stores | Demand has not been registered yet |  |  |  | Proposal has not been approved yet | [16 empty] | 0 | [7 empty] | 100116211003
15 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00085 | 2023-07-29 | 29/07/2023 | 1 | 539809941190 | Cable PVC insulated, armoured, unscreened, underground Railway signaling, copper cable of size 12C X 1.5 sqmm as per specification no.IRS:S-63/2014 (Rev 4.0) or latest. (Inspection by RDSO) | 2000 | MTR | 383740 | 383740 | Sr. Scale | 43167304 | SR-CN/MS | Demand Approved & Forwarded to Purchase Unit: - on 29/07/23 |  | Stores | Demand has not been registered yet |  |  |  | Proposal has not been approved yet | [16 empty] | 0 | [7 empty] | 100116211003
16 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00087 | 2023-07-29 | 29/07/2023 | 1 | 564681510123 | Supply of Double Digit Multi Lamp Route Indicator (LED Type). 1) To indicate 0-99 & 2A -2Nos, 2) 0-99, 2A & M-2Nos, Specification as per Annexure-A. Firm must provide Housing Rack along with MLRI to.... | 4 | Nos. | 167296 | 167296 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 29/07/23 | 90 | Stores | Demand has been registered with File no 90236706 dt.31/07/2023 | Tender - Normal | 90236706 | 31-07-2023 | Proposal Approved with 90236706 dt.31-07-2023 | 90236706 | 03/08/2023 | 21/08/2023 | Tender Finalized | [12 empty] | 0
17 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00087 | 2023-07-29 | 29/07/2023 | 1 | 564681510123 | Supply of Double Digit Multi Lamp Route Indicator (LED Type). 1) To indicate 0-99 & 2A -2Nos, 2) 0-99, 2A & M-2Nos, Specification as per Annexure-A. Firm must provide Housing Rack along with MLRI to.... | 4 | Nos. | 167296 | 167296 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 29/07/23 | 90 | Stores | Demand has been registered with File no 90236706 dt.31/07/2023 | Tender - Normal | 90236706A | 29-09-2023 | Proposal Approved with 90236706A dt.29-09-2023 | 90236706A | 12/10/2023 | 01/11/2023 | Tender Finalized | AGARWAL ELECTROSAFE WORKS PRIVATE LIMITED-HOWRAH | AGARWAL ELECTROSAFE WORKS PRIVATE LIMITED-HOWRAH | 90236706101822 | 10/11/2023 | 001 | 564681510123 | Supply of Double Digit Multi Lamp Route Indicator (LED Type). 1) To indicate 0-99 & 2A -2Nos, 2) 0-99, 2A & M-2Nos, Specification as per Annexure-A. Firm must provide Housing Rack along with MLRI to.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 4 | Nos. | 69677.82 | 278711.28 | 09-01-2024 | 4 | 278711.28
18 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00089 | 2023-08-18 | 18/08/2023 | 1 | 560604104278 | Transformer rectifier 110V AC/24VDC / 2 Amps capacity as per specification No.IRS.S. 91/2014 ver 1.0 or Latest. Make: Make: GAEC, Pranava Electronics, Electrostar only accepted. Inspection by RITES.... | 40 | Nos. | 481440 | 481440 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 18/08/23 | 90 | Stores | Demand has been registered with File no 90236923 dt.21/08/2023 | Tender - Normal | 90236903 | 21-08-2023 | Proposal Approved with 90236903 dt.21-08-2023 | 90236903 | 24/02/2024 | 20/03/2024 | Tender Finalized | ELECTROSTAR SIGNALLING AND POWER EQUIPMENTS PRIVATE LIMITED-KOLKATA | ELECTROSTAR SIGNALLING AND POWER EQUIPMENTS PRIVATE LIMITED-KOLKATA | 90236903100656 | 13/04/2024 | 001 | 560604104278 | Transformer rectifier 110V AC/24VDC / 2 Amps capacity as per specification No.IRS.S. 91/2014 ver 1.0 or Latest. Make: GAEC, Pranava Electronics, Electrostar only accepted. Firm-s offered Make/ Model: .... | SR | 027534 | SSE/SIG/SRM/PER, SR | 24 | Nos. | 10763.96 | 258335.04 | 12-07-2024 | 24 | 258335.04
19 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00089 | 2023-08-18 | 18/08/2023 | 1 | 560604104278 | Transformer rectifier 110V AC/24VDC / 2 Amps capacity as per specification No.IRS.S. 91/2014 ver 1.0 or Latest. Make: Make: GAEC, Pranava Electronics, Electrostar only accepted. Inspection by RITES.... | 40 | Nos. | 481440 | 481440 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 18/08/23 | 90 | Stores | Demand has been registered with File no 90236923 dt.21/08/2023 | Tender - Normal | 90236903 | 21-08-2023 | Proposal Approved with 90236903 dt.21-08-2023 | 90236903 | 24/02/2024 | 20/03/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90236903100657 | 13/04/2024 | 001 | 560604104278 | Transformer rectifier 110V AC/24VDC / 2 Amps capacity as per specification No.IRS.S. 91/2014 ver 1.0 or Latest. Make: GAEC, Pranava Electronics, Electrostar only accepted. Firm-s offered Make/ Model: .... | SR | 027534 | SSE/SIG/SRM/PER, SR | 16 | Nos. | 10763.96 | 172223.36 | 15-07-2024 | 16 | 172223.36 | 000922 | 20/11/2024 | Delivery Period End
20 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00090 | 2023-08-18 | 18/08/2023 | 1 | 560607670040 | Transformer rectifier 110V AC/24VDC / 5 Amps capacity as per specification No.IRS.S. 91/2014 ver 1.0 or Latest. Make: GAEC, Pranava Electronics, Electrostar only accepted. Inspection by RITES. | 70 | Nos. | 903490 | 903490 | JAG | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 18/08/23 | 90 | Stores | Demand has been registered with File no 90236903 dt.18/08/2023 | Tender - Normal | 90236903 | 21-08-2023 | Proposal Approved with 90236903 dt.21-08-2023 | 90236903 | 24/02/2024 | 20/03/2024 | Tender Finalized | ELECTROSTAR SIGNALLING AND POWER EQUIPMENTS PRIVATE LIMITED-KOLKATA | ELECTROSTAR SIGNALLING AND POWER EQUIPMENTS PRIVATE LIMITED-KOLKATA | 90236903100656 | 13/04/2024 | 002 | 560607670040 | Transformer rectifier 110V AC/24VDC / 5 Amps capacity as per specification No.IRS.S. 91/2014 ver 1.0 or Latest. Make: GAEC, Pranava Electronics, Electrostar only accepted. Inspection by RITES. Firm-s.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 48 | Nos. | 15011.96 | 720574.08 | 12-07-2024 | 48 | 720574.08
21 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00090 | 2023-08-18 | 18/08/2023 | 1 | 560607670040 | Transformer rectifier 110V AC/24VDC / 5 Amps capacity as per specification No.IRS.S. 91/2014 ver 1.0 or Latest. Make: GAEC, Pranava Electronics, Electrostar only accepted. Inspection by RITES. | 70 | Nos. | 903490 | 903490 | JAG | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 18/08/23 | 90 | Stores | Demand has been registered with File no 90236903 dt.18/08/2023 | Tender - Normal | 90236903 | 21-08-2023 | Proposal Approved with 90236903 dt.21-08-2023 | 90236903 | 24/02/2024 | 20/03/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90236903100657 | 13/04/2024 | 002 | 560607670040 | Transformer rectifier 110V AC/24VDC / 5 Amps capacity as per specification No.IRS.S. 91/2014 ver 1.0 or Latest. Make: GAEC, Pranava Electronics, Electrostar only accepted. Inspection by RITES. Firm-s.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 22 | Nos. | 15011.96 | 330263.12 | 15-07-2024 | 22 | 330263.12 | 000922 | 20/11/2024 | Delivery Period End
22 | 027534 | SSE/SIG/SRM/PER, SR | NO | Umbrella Item No. 874d/UW2 of PB 22-23 | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00091 | 2023-09-22 | 22/09/2023 | 1 | 570106540068 | All In One PC with 21.5 inch IPS Display, minimum Intel Core i5 12400 Processor, Windows 11 pro 64 OS, Chipset Intel B660, 2.5Ghz Base Frequency up to 4.4Ghz, 12 MB cache, 6 Cores, UHD Graphics card 7.... | 5 | Nos. | 299985 | 299985 | Sr. Scale | 29333304 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 22/09/23 | 90 | Stores | Demand has been registered with File no 90237218 dt.26/09/2023 | GeM Coverage PO | 90237218 | 30-10-2023 | Proposal Approved with 90237218 dt.30-10-2023 |  |  |  |  | KALAPURNA ASSOCIATES-CHENNAI | KALAPURNA ASSOCIATES-CHENNAI | 90237218201779 | 01/11/2023 | 001 | 570106540068 | acer Intel Core i5 All in One PC with 23.8 Inch Display/ Windows 11 Professional Brand: acer (Detailed Description/Specification as per Product # 1 of GeM Contract No. GEMC-511687751956793 dt.26/10/20.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 5 | Nos. | 57039 | 285195 | 17-02-2024 | 5 | 285195 | 000311 | 14/05/2024 | Delivery Period End | 100133221003
23 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00092 | 2023-08-14 | 14/08/2023 | 1 | 560402480101 | HIGH AVAILABILLITY SINGLE SECTION DIGITAL AXLE COUNTERS (HASSDAC)WITH DUAL SENSOR SYSTEM AS PER RDSO/SPN/177/2012 VER.3 OR LATEST THIS INCLUDES THE SUPPLY OF HIGH FREQUENCY WEB MOUNTING TYPE TX COIL/R.... | 1 | Set | 811840 | 811840 | JAG | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 14/08/23 | 90 | Stores | Demand has been registered with File no 90236868 dt.16/08/2023 | Tender - Normal | 90236868 | 16-08-2023 | Proposal Approved with 90236868 dt.16-08-2023 | 90236868 | 17/08/2023 | 05/09/2023 | Tender Finalized | [12 empty] | 0
24 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00092 | 2023-08-14 | 14/08/2023 | 1 | 560402480101 | HIGH AVAILABILLITY SINGLE SECTION DIGITAL AXLE COUNTERS (HASSDAC)WITH DUAL SENSOR SYSTEM AS PER RDSO/SPN/177/2012 VER.3 OR LATEST THIS INCLUDES THE SUPPLY OF HIGH FREQUENCY WEB MOUNTING TYPE TX COIL/R.... | 1 | Set | 811840 | 811840 | JAG | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 14/08/23 | 90 | Stores | Demand has been registered with File no 90236868 dt.16/08/2023 | Tender - Normal | 90236868A | 29-09-2023 | Proposal Approved with 90236868A dt.29-09-2023 | 90236868A | 12/10/2023 | 07/11/2023 | Tender Finalized | GAINWELL AGENCIES-NEW DELHI | GAINWELL AGENCIES-NEW DELHI | 90236868101863 | 20/11/2023 | 001 | 560402480101 | HIGH AVAILABILITY SINGLE SECTION DIGITAL AXLE COUNTERS (HASSDAC)WITH DUAL SENSOR SYSTEM AS PER RDSO/SPN/177/2012 VER.3 OR LATEST THIS INCLUDES THE SUPPLY OF HIGH FREQUENCY WEB MOUNTING TYPE TX COIL/RX.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 1 | Set | 808300 | 808300 | 19-01-2024 | 1 | 808300
25 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00093 | 2023-08-28 | 28/08/2023 | 1 | 560409420031 | Signal Conditioner Card No.1 (SCC1) for CEL MAKE HASSDAC as per RDSO Specification No.RDSO/SPN/177/2012 with version 3 or latest. | 10 | Nos. | 389400 | 389400 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 28/08/23 | 90 | Stores | Demand has been registered with File no 90237027 dt.30/08/2023 | Tender - Normal | 90237061 | 08-09-2023 | Proposal Approved with 90237061 dt.08-09-2023 | 90237061 | 02/10/2023 | 27/10/2023 | Tender Finalized | GAINWELL AGENCIES-NEW DELHI | GAINWELL AGENCIES-NEW DELHI | 90237061100623 | 08/04/2024 | 009 | 560409420031 | Signal Conditioner Card No.1 (SCC1) for CEL MAKE HASSDAC as per RDSO Specification No.RDSO/SPN/177/2012 with version 3 or latest. Firm-s offered Make/ Model: Central Electronics Limited; Firm's offere.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 37760 | 377600 | 07-07-2024 | 10 | 377600
26 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00094 | 2023-08-28 | 28/08/2023 | 1 | 560404260128 | Signal Conditioner Card No.2 (SCC2) for CEL MAKE HASSDAC as per RDSO Specification No.RDSO/SPN/177/2012 with version 3 or latest. | 10 | Nos. | 389400 | 389400 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 28/08/23 | 90 | Stores | Demand has been registered with File no 90237026 dt.30/08/2023 | Tender - Normal | 90237061 | 08-09-2023 | Proposal Approved with 90237061 dt.08-09-2023 | 90237061 | 02/10/2023 | 27/10/2023 | Tender Finalized | GAINWELL AGENCIES-NEW DELHI | GAINWELL AGENCIES-NEW DELHI | 90237061100623 | 08/04/2024 | 004 | 560404260128 | Signal Conditioner Card No.2 (SCC2) for CEL MAKE HASSDAC as per RDSO Specification No.RDSO/SPN/177/2012 with version 3 or latest. Firm-s offered Make/ Model: Central Electronics Limited; Firm's offer.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 37760 | 377600 | 07-07-2024 | 10 | 377600
27 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00095 | 2023-08-28 | 28/08/2023 | 1 | 560407390023 | Event Logger Card for CEL MAKE HASSDAC as per RDSO Specification No.RDSO/SPN/177/2012 with version 3 or latest. | 10 | Nos. | 354000 | 354000 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 28/08/23 | 90 | Stores | Demand has been registered with File no 90237011 dt.30/08/2023 | Tender - Normal | 90237061 | 08-09-2023 | Proposal Approved with 90237061 dt.08-09-2023 | 90237061 | 02/10/2023 | 27/10/2023 | Tender Finalized | GAINWELL AGENCIES-NEW DELHI | GAINWELL AGENCIES-NEW DELHI | 90237061100623 | 08/04/2024 | 007 | 560407390023 | Event Logger Card for CEL MAKE HASSDAC as per RDSO Specification No.RDSO/SPN/177/2012 with version 3 or latest. Firm-s offered Make/ Model: Central Electronics Limited; Firm's offered item - Event Log.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 37760 | 377600 | 07-07-2024 | 10 | 377600
28 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00096 | 2023-09-08 | 08/09/2023 | 1 | 560401560022 | Modem Card for CEL MAKE HASSDAC as per RDSO Specification No.RDSO/SPN/177/2012 with version 3 or latest. | 10 | Nos. | 365800 | 365800 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237061 dt.08/09/2023 | Tender - Normal | 90237061 | 08-09-2023 | Proposal Approved with 90237061 dt.08-09-2023 | 90237061 | 02/10/2023 | 27/10/2023 | Tender Finalized | GAINWELL AGENCIES-NEW DELHI | GAINWELL AGENCIES-NEW DELHI | 90237061100623 | 08/04/2024 | 003 | 560401560022 | Modem Card for CEL MAKE HASSDAC as per RDSO Specification No.RDSO/SPN/177/2012 with version 3 or latest. Firm-s offered Make/ Model: Central Electronics Limited; Firms offered item - Modem Card for HA.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 37760 | 377600 | 07-07-2024 | 10 | 377600
29 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00097 | 2023-08-28 | 28/08/2023 | 1 | 560404691486 | Relay Drive Card for CEL MAKE HASSDAC as per RDSO Specification No.RDSO/SPN/177/2012 with version 3 or latest. | 10 | Nos. | 389400 | 389400 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 28/08/23 | 90 | Stores | Demand has been registered with File no 90237022 dt.30/08/2023 | Tender - Normal | 90237061 | 08-09-2023 | Proposal Approved with 90237061 dt.08-09-2023 | 90237061 | 02/10/2023 | 27/10/2023 | Tender Finalized | GAINWELL AGENCIES-NEW DELHI | GAINWELL AGENCIES-NEW DELHI | 90237061100623 | 08/04/2024 | 005 | 560404691486 | Relay Drive Card for CEL MAKE HASSDAC as per RDSO Specification No.RDSO/SPN/177/2012 with version 3 or latest. Firm-s offered Make/ Model: Central Electronics Limited; Firm's offered item - Relay Dri.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 37760 | 377600 | 07-07-2024 | 10 | 377600
30 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00098 | 2023-09-08 | 08/09/2023 | 1 | 560400024931 | Reset card of Reset Box for CEL MAKE HASSDAC as per RDSO Specification No.RDSO/SPN/177/2012 with version 3 or latest. | 10 | Nos. | 188000 | 188000 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237062 dt.08/09/2023 | Tender - Normal | 90237061 | 08-09-2023 | Proposal Approved with 90237061 dt.08-09-2023 | 90237061 | 02/10/2023 | 27/10/2023 | Tender Finalized | GAINWELL AGENCIES-NEW DELHI | GAINWELL AGENCIES-NEW DELHI | 90237061100623 | 08/04/2024 | 002 | 560400024931 | Reset card of Reset Box for CEL MAKE HASSDAC as per RDSO Specification No.RDSO/SPN/177/2012 with version 3 or latest. Firm-s offered Make/ Model: Central Electronics Limited; Firm's offered Item - Res.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 19116 | 191160 | 07-07-2024 | 10 | 191160
31 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00099 | 2023-09-08 | 08/09/2023 | 1 | 560406700041 | Auto Reset Card for CEL MAKE HASSDAC as per RDSO Specification No.RDSO/SPN/177/2012 with version 3 or latest. | 10 | Nos. | 188800 | 188800 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237063 dt.08/09/2023 | Tender - Normal | 90237061 | 08-09-2023 | Proposal Approved with 90237061 dt.08-09-2023 | 90237061 | 02/10/2023 | 27/10/2023 | Tender Finalized | GAINWELL AGENCIES-NEW DELHI | GAINWELL AGENCIES-NEW DELHI | 90237061100623 | 08/04/2024 | 006 | 560406700041 | Auto Reset Card for CEL MAKE HASSDAC as per RDSO Specification No.RDSO/SPN/177/2012 with version 3 or latest. Firm-s offered Make/ Model: Central Electronics Limited; Firm's offered item - Auto RESET.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 19234 | 192340 | 07-07-2024 | 10 | 192340
32 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00100 | 2023-08-28 | 28/08/2023 | 1 | 560407690020 | Interface card for Reset Box for HASSDAC Motherboard for CEL MAKE HASSDAC as per RDSO Specification No.RDSO/SPN/177/2012 with version 3 or latest. | 10 | Nos. | 295000 | 295000 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 28/08/23 | 90 | Stores | Demand has been registered with File no 90237019 dt.30/08/2023 | Tender - Normal | 90237061 | 08-09-2023 | Proposal Approved with 90237061 dt.08-09-2023 | 90237061 | 02/10/2023 | 27/10/2023 | Tender Finalized | GAINWELL AGENCIES-NEW DELHI | GAINWELL AGENCIES-NEW DELHI | 90237061100623 | 08/04/2024 | 008 | 560407690020 | Interface card for Reset Box for HASSDAC Motherboard for CEL MAKE HASSDAC as per RDSO Specification No.RDSO/SPN/177/2012 with version 3 or latest. Firm-s offered Make/ Model: Central Electronics Limit.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 29500 | 295000 | 07-07-2024 | 10 | 295000
33 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00101 | 2023-09-08 | 08/09/2023 | 1 | 539817581104 | Web Detector (each set consists of 2 Nos. of TX and 2 Nos. of RX) for CEL make HASSDAC Systems as per RDSO Specn.No.RDSO/SPN/177/2012 ver. 3 or latest. (Phase Reversal Type) | 18 | Set | 934560 | 934560 | JAG | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237079 dt.08/09/2023 | Tender - Normal | 90237061 | 08-09-2023 | Proposal Approved with 90237061 dt.08-09-2023 | 90237061 | 02/10/2023 | 27/10/2023 | Tender Finalized | GAINWELL AGENCIES-NEW DELHI | GAINWELL AGENCIES-NEW DELHI | 90237061100623 | 08/04/2024 | 001 | 539817581104 | Web Detector (each set consists of 2 Nos. of TX and 2 Nos. of RX) for CEL make HASSDAC Systems as per RDSO Specn.No.RDSO/SPN/177/2012 ver. 3 or latest. (Phase Reversal Type) Firm-s offered Make/ Model.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 18 | Set | 51920 | 934560 | 07-07-2024 | 18 | 934560
34 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00102 | 2023-09-08 | 08/09/2023 | 1 | 569008650040 | Supply of Processor card suitable for M/s Efftronics make Data logger as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Inspection by RDSO. | 10 | Nos. | 472000 | 472000 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237066 dt.08/09/2023 | Tender - Normal | 90237059 | 08-09-2023 | Proposal Approved with 90237059 dt.08-09-2023 | 90237059 | 28/12/2023 | 30/01/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90237059100636 | 10/04/2024 | 001 | 569008650040 | Supply of Processor card suitable for M/s Efftronics make Data logger as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Firm-s offered Make/ Model: EFFTRONICS SYSTEMS PVT LTD and HSN Code: 84715000 | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 47200 | 472000 | 09-07-2024 | 10 | 472000
35 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00102 | 2023-09-08 | 08/09/2023 | 1 | 569008650040 | Supply of Processor card suitable for M/s Efftronics make Data logger as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Inspection by RDSO. | 10 | Nos. | 472000 | 472000 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237066 dt.08/09/2023 |  | 90237066 | 27-12-2023 | Proposal has not been approved yet with 90237066 dt.27-12-2023 | [16 empty] | 0
36 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00103 | 2023-09-08 | 08/09/2023 | 1 | 569008650052 | Supply of Communication Card suitable for M/s Efftronics make Data logger as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Inspection by RDSO. | 10 | Nos. | 262550 | 262550 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237067 dt.08/09/2023 | Tender - Normal | 90237059 | 08-09-2023 | Proposal Approved with 90237059 dt.08-09-2023 | 90237059 | 28/12/2023 | 30/01/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90237059100636 | 10/04/2024 | 002 | 569008650052 | Supply of Communication Card suitable for M/s Efftronics make Data logger as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Firm-s offered Make/ Model: EFFTRONICS SYSTEMS PVT LTD and HSN Code: 84715000 | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 26255 | 262550 | 09-07-2024 | 10 | 262550
37 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00104 | 2023-09-08 | 08/09/2023 | 1 | 569008650064 | Supply of Power supply Card suitable for M/s Efftronics make Data logger as per Spec:IRS:S-99/2006 (Amdt-3) or latest. Inspection by RDSO. | 10 | Nos. | 110000 | 110000 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237059 dt.08/09/2023 | Tender - Normal | 90237059 | 08-09-2023 | Proposal Approved with 90237059 dt.08-09-2023 | 90237059 | 28/12/2023 | 30/01/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90237059100636 | 10/04/2024 | 003 | 569008650064 | Supply of Power supply Card suitable for M/s Efftronics make Data logger as per Spec:IRS:S-99/2006 (Amdt-3) or latest. Firm-s offered Make/ Model: EFFTRONICS SYSTEMS PVT LTD and HSN Code: 84715000 | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 10999.96 | 109999.6 | 09-07-2024 | 10 | 109999.6
38 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00105 | 2023-09-08 | 08/09/2023 | 1 | 569008650076 | Supply of Analog Card without controller suitable for M/s Efftronics make Data logger as per Spec:IRS:S-99/2006 (Amdt-3) or latest. Inspection by RDSO. | 10 | Nos. | 236000 | 236000 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237065 dt.08/09/2023 | Tender - Normal | 90237059 | 08-09-2023 | Proposal Approved with 90237059 dt.08-09-2023 | 90237059 | 28/12/2023 | 30/01/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90237059100636 | 10/04/2024 | 004 | 569008650076 | Supply of Analog Card without controller suitable for M/s Efftronics make Data logger as per Spec:IRS:S-99/2006 (Amdt-3) or latest. Firm-s offered Make/ Model: EFFTRONICS SYSTEMS PVT LTD and HSN Code:.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 23600 | 236000 | 09-07-2024 | 10 | 236000
39 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00106 | 2023-09-08 | 08/09/2023 | 1 | 569008650088 | Supply of Analog scanner Card with controller suitable for M/s Efftronics make Data logger as per Spec:IRS:S-99/2006 (Amdt-3) or latest. Inspection by RDSO. | 10 | Nos. | 295000 | 295000 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237064 dt.08/09/2023 | Tender - Normal | 90237059 | 08-09-2023 | Proposal Approved with 90237059 dt.08-09-2023 | 90237059 | 28/12/2023 | 30/01/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90237059100636 | 10/04/2024 | 005 | 569008650088 | Supply of Analog scanner Card with controller suitable for M/s Efftronics make Data logger as per Spec:IRS:S-99/2006 (Amdt-3) or latest. Firm-s offered Make/ Model: EFFTRONICS SYSTEMS PVT LTD and HSN .... | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 29500 | 295000 | 09-07-2024 | 10 | 295000
40 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00107 | 2023-09-08 | 08/09/2023 | 1 | 569008650090 | Supply of Digital Interface card suitable for M/s Efftronics make Data logger as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Inspection by RDSO. | 10 | Nos. | 159990 | 159990 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237078 dt.08/09/2023 | Tender - Normal | 90237059 | 08-09-2023 | Proposal Approved with 90237059 dt.08-09-2023 | 90237059 | 28/12/2023 | 30/01/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90237059100636 | 10/04/2024 | 006 | 569008650090 | Supply of Digital Interface card suitable for M/s Efftronics make Data logger as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Firm-s offered Make/ Model: EFFTRONICS SYSTEMS PVT LTD and HSN Code:8471500.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 15999.62 | 159996.2 | 09-07-2024 | 10 | 159996.2
41 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00108 | 2023-09-08 | 08/09/2023 | 1 | 569008650106 | Supply of Dual Modem E1 Converter suitable for M/s Efftronics make Data logger as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Inspection by Consignee. | 10 | Nos. | 394120 | 394120 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237060 dt.08/09/2023 | Tender - Normal | 90237059 | 08-09-2023 | Proposal Approved with 90237059 dt.08-09-2023 | 90237059 | 28/12/2023 | 30/01/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90237059100636 | 10/04/2024 | 007 | 569008650106 | Supply of Dual Modem E1 Converter suitable for M/s Efftronics make Data logger as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Firm-s offered Make/ Model: EFFTRONICS SYSTEMS PVT LTD and HSN Code:851762 | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 39412 | 394120 | 09-07-2024 | 10 | 394120
42 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00109 | 2023-09-08 | 08/09/2023 | 1 | 569008650118 | Supply of GDT card suitable for M/s Efftronics make Data logger system as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Inspection by Consignee. | 20 | Nos. | 136680 | 136680 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237077 dt.08/09/2023 | Tender - Normal | 90237059 | 08-09-2023 | Proposal Approved with 90237059 dt.08-09-2023 | 90237059 | 28/12/2023 | 30/01/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90237059100636 | 10/04/2024 | 008 | 569008650118 | Supply of GDT card suitable for M/s Efftronics make Data logger system as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Firm-s offered Make/ Model: EFFTRONICS SYSTEMS PVT LTD and HSN Code:84715000 | SR | 027534 | SSE/SIG/SRM/PER, SR | 20 | Nos. | 6836.92 | 136738.4 | 09-07-2024 | 20 | 136738.4
43 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00110 | 2023-09-08 | 08/09/2023 | 1 | 569008650120 | Supply of 64 Digital input stack card suitable for M/s Efftronics make Data logger as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Inspection by RDSO. | 10 | Nos. | 236000 | 236000 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237076 dt.08/09/2023 | Tender - Normal | 90237059 | 08-09-2023 | Proposal Approved with 90237059 dt.08-09-2023 | 90237059 | 28/12/2023 | 30/01/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90237059100636 | 10/04/2024 | 009 | 569008650120 | Supply of 64 Digital input stack card suitable for M/s Efftronics make Data logger as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Firm-s offered Make/ Model: EFFTRONICS SYSTEMS PVT LTD and HSN Code:84.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 23600 | 236000 | 09-07-2024 | 10 | 236000
44 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00111 | 2023-09-08 | 08/09/2023 | 1 | 569008650131 | Supply of Analog protection strip PCB card suitable for M/s Efftronics make Data logger as per Spec:IRS:S-99/2006 (Amdt-3) or latest. Inspection by Consignee. | 10 | Nos. | 16520 | 16520 | Jr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237075 dt.08/09/2023 | Tender - Normal | 90237059 | 08-09-2023 | Proposal Approved with 90237059 dt.08-09-2023 | 90237059 | 28/12/2023 | 30/01/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90237059100636 | 10/04/2024 | 010 | 569008650131 | Supply of Analog protection strip PCB card suitable for M/s Efftronics make Data logger as per Spec:IRS:S-99/2006 (Amdt-3) or latest. Firm-s offered Make/ Model: EFFTRONICS SYSTEMS PVT LTD and HSN Cod.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 1652 | 16520 | 09-07-2024 | 10 | 16520
45 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00112 | 2023-09-08 | 08/09/2023 | 1 | 569008650143 | Supply of Processor card suitable for Efftronics make RTU as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Inspection by RDSO. | 10 | Nos. | 472000 | 472000 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237074 dt.08/09/2023 | Tender - Normal | 90237059 | 08-09-2023 | Proposal Approved with 90237059 dt.08-09-2023 | 90237059 | 28/12/2023 | 30/01/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90237059100636 | 10/04/2024 | 011 | 569008650143 | Supply of Processor card suitable for Efftronics make RTU as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Firm-s offered Make/ Model: EFFTRONICS SYSTEMS PVT LTD and HSN Code:84715000 | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 47200 | 472000 | 09-07-2024 | 10 | 472000
46 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00113 | 2023-09-08 | 08/09/2023 | 1 | 569008650155 | Supply of Dual Modem Card suitable for Efftronics make RTU as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Inspection by RDSO. | 10 | Nos. | 318600 | 318600 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237073 dt.08/09/2023 | Tender - Normal | 90237059 | 08-09-2023 | Proposal Approved with 90237059 dt.08-09-2023 | 90237059 | 28/12/2023 | 30/01/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90237059100636 | 10/04/2024 | 012 | 569008650155 | Supply of Dual Modem Card suitable for Efftronics make RTU as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Firm-s offered Make/ Model: EFFTRONICS SYSTEMS PVT LTD and HSN Code: 8471 5000 | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 31860 | 318600 | 09-07-2024 | 10 | 318600
47 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00114 | 2023-09-08 | 08/09/2023 | 1 | 569008650167 | Supply of Power supply Card suitable for Efftronics make RTU as per Spec: IRS: S-99/2006 (Amdt-3) or latest. Inspection by RDSO. | 10 | Nos. | 110000 | 110000 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237072 dt.08/09/2023 | Tender - Normal | 90237059 | 08-09-2023 | Proposal Approved with 90237059 dt.08-09-2023 | 90237059 | 28/12/2023 | 30/01/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90237059100636 | 10/04/2024 | 013 | 569008650167 | Supply of Power supply Card suitable for Efftronics make RTU as per Spec: IRS: S-99/2006 (Amdt-3) or latest. Firm-s offered Make/ Model: EFFTRONICS SYSTEMS PVT LTD and HSN Code:84715000 | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 10999.96 | 109999.6 | 09-07-2024 | 10 | 109999.6
48 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00115 | 2023-09-08 | 08/09/2023 | 1 | 569008650179 | Supply of Analog Card without controller suitable for Efftronics make RTU as per Spec: IRS: S-99/2006 (Amdt-3) or latest. Inspection by RDSO. | 10 | Nos. | 236000 | 236000 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237071 dt.08/09/2023 | Tender - Normal | 90237059 | 08-09-2023 | Proposal Approved with 90237059 dt.08-09-2023 | 90237059 | 28/12/2023 | 30/01/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90237059100636 | 10/04/2024 | 014 | 569008650179 | Supply of Analog Card without controller suitable for Efftronics make RTU as per Spec: IRS: S-99/2006 (Amdt-3) or latest. Firm-s offered Make/ Model: EFFTRONICS SYSTEMS PVT LTD and HSN Code:84715000 | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 23600 | 236000 | 09-07-2024 | 10 | 236000
49 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00116 | 2023-09-08 | 08/09/2023 | 1 | 569008650180 | Supply of Analog scanner Card with controller suitable for Efftronics make RTU as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Inspection by RDSO. | 10 | Nos. | 295000 | 295000 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237070 dt.08/09/2023 | Tender - Normal | 90237059 | 08-09-2023 | Proposal Approved with 90237059 dt.08-09-2023 | 90237059 | 28/12/2023 | 30/01/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90237059100636 | 10/04/2024 | 015 | 569008650180 | Supply of Analog scanner Card with controller suitable for Efftronics make RTU as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Firm-s offered Make/ Model: EFFTRONICS SYSTEMS PVT LTD and HSN Code:847150.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 10 | Nos. | 29500 | 295000 | 09-07-2024 | 10 | 295000
50 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00117 | 2023-09-08 | 08/09/2023 | 1 | 569008650192 | Supply of GDT card suitable for Efftronics make RTU system as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Inspection by Consignee. | 20 | Nos. | 136740 | 136740 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/09/23 | 90 | Stores | Demand has been registered with File no 90237069 dt.08/09/2023 | Tender - Normal | 90237059 | 08-09-2023 | Proposal Approved with 90237059 dt.08-09-2023 | 90237059 | 28/12/2023 | 30/01/2024 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90237059100636 | 10/04/2024 | 016 | 569008650192 | Supply of GDT card suitable for Efftronics make RTU system as per Spec: IRS:S-99/2006 (Amdt-3) or latest. Firm-s offered Make/ Model: EFFTRONICS SYSTEMS PVT LTD and HSN Code:84715000 | SR | 027534 | SSE/SIG/SRM/PER, SR | 20 | Nos. | 6836.92 | 136738.4 | 09-07-2024 | 20 | 136738.4
51 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00119 | 2023-09-14 | 14/09/2023 | 1 | 509000348620 | Small sized Valve Regulated Lead-Acid Batteries(SMF) with 12V/42AH Capacity confirming to JISC: 8702/1998 (Part 1,2&3) with latest amendments, with PPCP Container as per GEM ID 5116877-65990964025. .... | 60 | Nos. | 228000 | 228000 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 14/09/23 | 90 | Stores | Demand has been registered with File no 90237176 dt.15/09/2023 | GeM Coverage PO | 90237176 | 09-11-2023 | Proposal Approved with 90237176 dt.09-11-2023 |  |  |  |  | A J POWER CENTER, CHENNAI | A J POWER CENTER, CHENNAI | 90237176201825 | 10/11/2023 | 001 | 509000348620 | EXIDE Rechargeable Smf Lead Acid Battery 2 year Warranty Brand: EXIDE (Detailed Description/Specification as per Product # 1 of GeM Contract No. GEMC-511687779216074 dt.03/11/2023) | SR | 027534 | SSE/SIG/SRM/PER, SR | 60 | Nos. | 4028 | 241680 | 18-11-2023 | 60 | 241680 | 000112 | 21/02/2024 | Modification of Bank Details
52 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00120 | 2023-08-28 | 28/08/2023 | 1 | 560407020025 | Supply of Tx 21/25 KHZ coil assembly for GG tronic make HASSDAC as per RDSO specification No. RDSO/SPN/177/2012 with version 3.0 or latest. | 20 | Nos. | 868480 | 868480 | JAG | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 28/08/23 | 90 | Stores | Demand has been registered with File no 90237013 dt.30/08/2023 | Tender - Normal | 90237012 | 05-09-2023 | Proposal Approved with 90237012 dt.05-09-2023 | 90237012 | 02/10/2023 | 18/10/2023 | Tender Finalized | EARTH RAIL INFRA-NEW DELHI | EARTH RAIL INFRA-NEW DELHI | 90237012101898 | 23/11/2023 | 002 | 560407020025 | Supply of Tx 21/25 KHZ coil assembly for GG tronic make HASSDAC as per RDSO specification No. RDSO/SPN/177/2012 with version 3.0 or latest. Firm-s offered Make/ Model: GGT | SR | 027534 | SSE/SIG/SRM/PER, SR | 20 | Nos. | 44604 | 892080 | 10-04-2024 | 20 | 892080 | 000152 | 08/03/2024 | Delivery Period End
53 | 027534 | SSE/SIG/SRM/PER, SR | YES |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00121 | 2023-08-28 | 28/08/2023 | 1 | 560403031510 | Supply of Rx 21/25 KHZ coil assembly for GG tronic make HASSDAC as per RDSO specification No. RDSO/SPN/177/2012 with version 3.0 or latest. | 20 | Nos. | 868480 | 868480 | JAG | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 28/08/23 | 90 | Stores | Demand has been registered with File no 90237012 dt.30/08/2023 | Tender - Normal | 90237012 | 05-09-2023 | Proposal Approved with 90237012 dt.05-09-2023 | 90237012 | 02/10/2023 | 18/10/2023 | Tender Finalized | EARTH RAIL INFRA-NEW DELHI | EARTH RAIL INFRA-NEW DELHI | 90237012101898 | 23/11/2023 | 001 | 560403031510 | Supply of Rx 21/25 KHZ coil assembly for GG tronic make HASSDAC as per RDSO specification No. RDSO/SPN/177/2012 with version 3.0 or latest. Firm-s offered Make/ Model: GGT | SR | 027534 | SSE/SIG/SRM/PER, SR | 20 | Nos. | 44604 | 892080 | 10-04-2024 | 20 | 892080 | 000152 | 08/03/2024 | Delivery Period End
54 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00122 | 2023-08-31 | 31/08/2023 | 1 | 810800350051 | Loctite Medium strength surface insensitive Thread Locking Adhesive, Size 50 milliliter Loctite R (LOCTITE 243) spec as per GEM ID 5116877-52790864150. Make Loclite, Annabond, Pidilite only accepted | 200 | Nos. | 155000 | 155000 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 31/08/23 | 90 | Stores | Demand has been registered with File no 90237045 dt.04/09/2023 | GeM Coverage PO | 90237045 | 04-10-2023 | Proposal Approved with 90237045 dt.04-10-2023 |  |  |  |  | VIMALSHRI ENTERPRISES-BINA | VIMALSHRI ENTERPRISES-BINA | 90237045201674 | 12/10/2023 | 001 | 810800350051 | Unbranded Medium strength Thread Locking Adhesive, Size 50 milliliter Brand: NA (Detailed Description/Specification as per Product # 1 of GeM Contract No. GEMC-511687784072377 dt.21/09/2023) | SR | 027534 | SSE/SIG/SRM/PER, SR | 200 | Nos. | 785 | 157000 | 06-10-2023 | 200 | 157000
55 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00123 | 2023-08-26 | 26/08/2023 | 1 | 560610600053 | Non Flammable Electronic Contact Cleaner in 500 ml Container Specification as per GEM ID 5116877-45627825864. Make WD-40, CRC, Hosa DeoxIT only accepted Inspection by consignee. | 200 | Nos. | 68000 | 68000 | Jr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 26/08/23 | 90 | Stores | Demand has been registered with File no 90237005 dt.28/08/2023 | GeM Coverage PO | 90237005 | 25-10-2023 | Proposal Approved with 90237005 dt.25-10-2023 |  |  |  |  | ROBUST AEROTECH PVT. LTD.-GREATER NOIDA | ROBUST AEROTECH PVT. LTD.-GREATER NOIDA | 90237005201743 | 30/10/2023 | 001 | 560610600053 | SPRAYSOL Non Flammable Electronic Contact Cleaner, Size 500 millimeter in Can Brand: SPRAYSOL (Detailed Description/Specification as per Product # 1 of GeM Contract No. GEMC-511687733321722 dt.18/10/2.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 200 | Nos. | 180 | 36000 | 02-11-2023 | 200 | 36000
56 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00124 | 2023-09-06 | 06/09/2023 | 1 | 539812840168 | SUPPLY OF B TYPE CHOKE COIL FOR SINGLE RAIL TRACK CIRCUIT ON 25KV, 50HZ, AC ELECTRIFIED SECTION AS PER RDSO SPECIFICATION IRS: S-65/83 AMD 3 OR LATEST. INSPECTION AGENCYRDSO | 400 | Nos. | 991200 | 991200 | JAG | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 06/09/23 | 90 | Stores | Demand has been registered with File no 90237054 dt.07/09/2023 | Tender - Normal | 90237054 | 07-09-2023 | Proposal Approved with 90237054 dt.07-09-2023 | 90237054 | 20/09/2023 | 08/01/2024 | Tender Finalized | SREE CHAND ELECTRICAL INDUSTRIES PVT. LTD.-KOLKATA | SREE CHAND ELECTRICAL INDUSTRIES PVT. LTD.-KOLKATA | 90237054100126 | 24/01/2024 | 001 | 539812840168 | SUPPLY OF B TYPE CHOKE COIL FOR SINGLE RAIL TRACK CIRCUIT ON 25KV, 50HZ, AC ELECTRIFIED SECTION AS PER RDSO SPECIFICATION IRS: S-65/83 AMD 3 OR LATEST. INSPECTION AGENCYRDSO Firm offer: same as above.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 400 | Nos. | 2239.64 | 895856 | 24-03-2024 | 400 | 895856
57 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00125 | 2023-09-07 | 07/09/2023 | 1 | 539811150053 | Non Deteriorating type Fuses Cylindrical 1.0 Amps for LED Aspect IRS: S-78/92. Make: Nandi, Bajeria, RBCO, NEO 4D. Inspection by RDSO | 4000 | Nos. | 274800 | 274800 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 07/09/23 | 90 | Stores | Demand has been registered with File no 90237057 dt.08/09/2023 | Tender - Normal | 90237057 | 08-09-2023 | Proposal Approved with 90237057 dt.08-09-2023 | 90237057 | 30/10/2023 | 06/11/2023 | Tender Finalized | NANDI ELECTRIC COMPANY-BANGALORE | BLUE BIRD TECHNICKS PVT LTD-KOLKATA | 90237057101810 | 09/11/2023 | 001 | 539811150053 | Non Deteriorating type Fuses Cylindrical 1.0 Amps for LED Aspect IRS: S-78/92. Make: Nandi, Bajeria, RBCO, NEO 4D. Inspection by RDSO Firm offer/Make:NANDI | SR | 027534 | SSE/SIG/SRM/PER, SR | 4000 | Nos. | 73.16 | 292640 | 09-02-2024 | 4000 | 292640 | 000025 | 10/01/2024 | Delivery Period End
58 | 027534 | SSE/SIG/SRM/PER, SR | NO | Umbrella Item No. 874d/UW2 of PB 22-23 | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00126 | 2023-09-20 | 20/09/2023 | 1 | 430800142395 | INFRARED THERMAL IMAGINE CAMERA AS PER RDSO SPEC TI/SPC/OHE/TIPS/1031(10/2013) MAKE FLIR MODEL NO E-60 OR SIMILAR, INSPECTION BY RITES/TPI AGENCY | 1 | Nos. | 633332 | 633332 | JAG | 29333304 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 20/09/23 | 90 | Stores | Demand has been registered with File no 90237210 dt.22/09/2023 | Tender - Normal | 90237210 | 29-09-2023 | Proposal Approved with 90237210 dt.29-09-2023 | 90237210 | 12/10/2023 | 07/11/2023 | Tender Finalized | GALAXY INTERNATIONAL-RAIPUR | GALAXY INTERNATIONAL-RAIPUR | 90237210101917 | 27/11/2023 | 001 | 430800142395 | INFRARED THERMAL IMAGINE CAMERA AS PER RDSO SPEC TI/SPC/OHE/TIPS/1031(10/2013) MAKE FLIR MODEL NO E-60 OR SIMILAR, INSPECTION BY RITES/TPI AGENCY Frmr offer:OUR OFFER MODEL IS 100% COMPLIED WITH RDSO .... | SR | 027534 | SSE/SIG/SRM/PER, SR | 1 | Nos. | 153400 | 153400 | 26-01-2024 | 1 | 153400 | 000957 | 29/11/2023 | INSPECTION: | 100133221003
59 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00127 | 2023-09-20 | 20/09/2023 | 1 | 658200030782 | Digital Storage Oscilloscope to measure bandwidth up to 50Mhz with 2 Analog, Sample rate 2GSa/s, 16 Digital Input Channel, Sampling rate 1GSa/s, Memory Depth-16Mpts, Display 7", OS :Windows-XP, Vista,.... | 1 | Nos. | 110000 | 110000 | Sr. Scale | 29333304 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 20/09/23 | 90 | Stores | Demand has been registered with File no 90237209 dt.22/09/2023 | GeM Coverage PO | 90237209 | 14-11-2023 | Proposal Approved with 90237209 dt.14-11-2023 |  |  |  |  | SWARG SYSTEMS & INSTRUMENTS, GANDHINAGAR | SWARG SYSTEMS & INSTRUMENTS, GANDHINAGAR | 90237209201850 | 16/11/2023 | 001 | 658200030782 | RIGOL Analog and Analog and Digital (Mixed Signal) 50 megaHertz Non -Windows Digital Storage Oscilloscope Brand: RIGOL (Detailed Description/Specification as per Product # 1 of GeM Contract No. GEMC-5.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 1 | Nos. | 40000 | 40000 | 10-12-2023 | [5 empty] | 100133221003
60 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00128 | 2023-09-14 | 14/09/2023 | 1 | 502355770055 | Signal Post Telephone with Talk Back facility operation voltage 12V DC +/-10% as per spec Tel/SPT/099, Make: Tummala, ACES, Indisco only accepted | 40 | Nos. | 230714 | 230714 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 14/09/23 | 90 | Stores | Demand has been registered with File no 90237175 dt.15/09/2023 | Tender - Normal | 90237175 | 29-09-2023 | Proposal Approved with 90237175 dt.29-09-2023 | 90237175 | 12/10/2023 | 09/11/2023 | Tender Finalized | INDUSTRIAL INSTRUMENTS AND CONTROLS-KANPUR | INDUSTRIAL INSTRUMENTS AND CONTROLS-KANPUR | 90237175101846 | 16/11/2023 | 001 | 502355770055 | Signal Post Telephone with Talk Back facility operation voltage 12V DC +/-10% as per spec Tel/SPT/099, Make: Tummala, ACES, Indisco only accepted Firm offer: same as above. Make:Indisco | SR | 027534 | SSE/SIG/SRM/PER, SR | 40 | Nos. | 5428 | 217120 | 15-03-2024 | 40 | 217120
61 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00131 | 2023-11-02 | 02/11/2023 | 1 | 561183521801 | PVC Cable of unsheathed insulated annealed tinned copper conductor single core multi strands 16/0.2 mm SC/ATC with colour Grey confirming to IRS.S.76/89 Amendment No.2 or latest. (1 Coil-100 Mtrs). | 50000 | MTR | 353500 | 353500 | Sr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 02/11/23 | 90 | Stores | Demand has been registered with File no 90237585 dt.06/11/2023 | Tender - Normal | 90237585 | 10-11-2023 | Proposal Approved with 90237585 dt.10-11-2023 | 90237585 | 19/12/2023 | 08/01/2024 | Tender Finalized | CYBELE INDUSTRIES LTD-CHENNAI | CYBELE INDUSTRIES LTD-CHENNAI | 90237585100125 | 24/01/2024 | 001 | 561183521801 | PVC Cable of unsheathed insulated annealed tinned copper conductor single core multi strands 16/0.2 mm SC/ATC with colour Grey confirming to IRS.S.76/89 Amendment No.2 or latest. (1 Coil-100 Mtrs). Fi.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 50000 | MTR | 6.87 | 343380 | 24-04-2024 | 50000 | 343380 | 000220 | 01/04/2024 | Delivery Period End
62 | 027534 | SSE/SIG/SRM/PER, SR | NO |  | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00133 | 2023-10-26 | 26/10/2023 | 1 | 551200012269 | Springs in set for KEY LOCK E-Type one set consisting of i) Tumbler spring to Drg. No. CWM 02806 - 03 Nos 2) Spring to Drg. No. CWM 03106-1No (Two items only) (Total quantity ward spring 1x2000=2000 N.... | 2000 | Set | 35940 | 35940 | Jr. Scale | 07053128 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 26/10/23 | 90 | Stores | Demand has been registered with File no 90237534 dt.30/10/2023 | Tender - Normal | 90237534 | 02-11-2023 | Proposal Approved with 90237534 dt.02-11-2023 | 90237534 | 02/11/2023 | 18/12/2023 | Tender Finalized | EASTERN TOOLS SYNDICATE-KOLKATA | EASTERN TOOLS SYNDICATE-KOLKATA | 90237534102114 | 28/12/2023 | 001 | 551200012269 | Springs in set for KEY LOCK E-Type one set consisting of i) Tumbler spring to Drg. No. CWM 02806 - 03 Nos 2) Spring to Drg. No. CWM 03106-1No (Two items only) (Total quantity ward spring 1x2000=2000 N.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 2000 | Set | 17.7 | 35400 | 27-03-2024 | 2000 | 35400
63 | 027534 | SSE/SIG/SRM/PER, SR | NO | Sr.DSTE/II/MAS Vide No.M/SG.242/LED/RE/2023-24 dt.02.10.2023 | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00137 | 2023-10-16 | 16/10/2023 | 1 | 56468039 | LED RED Signal Aspect Main Unit 110V AC retrofittable in existing CLS Housing and compatible with AC LED ECR as per RDSO Spec:RDSO/SPN/199/2010 Revision 1.1 | 200 | Nos. | 1770000 | 1770000 | SAG | 29333304 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 16/10/23 | 90 | Stores | Demand has been registered with File no 90237497 dt.26/10/2023 | Tender - Normal | 90237496 | 26-10-2023 | Proposal Approved with 90237496 dt.26-10-2023 | 90237496 | 14/12/2023 | 18/01/2024 | Tender Finalized | INSTAPOWER LTD-NEW DELHI | INSTAPOWER LTD-NEW DELHI | 90237496100137 | 28/01/2024 | 001 | 56468039 | LED RED Signal Aspect Main Unit 110V AC retrofittable in existing CLS Housing and compatible with AC LED ECR as per RDSO Spec:RDSO/SPN/199/2010 Revision 1.1 Firm-s offered Make/ Model: Instapower and.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 40 | Nos. | 8271.8 | 330872 | 28-03-2024 | 40 | 330872 |  |  |  | 100133211001
64 | 027534 | SSE/SIG/SRM/PER, SR | NO | Sr.DSTE/II/MAS Vide No.M/SG.242/LED/RE/2023-24 dt.02.10.2023 | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00137 | 2023-10-16 | 16/10/2023 | 1 | 56468039 | LED RED Signal Aspect Main Unit 110V AC retrofittable in existing CLS Housing and compatible with AC LED ECR as per RDSO Spec:RDSO/SPN/199/2010 Revision 1.1 | 200 | Nos. | 1770000 | 1770000 | SAG | 29333304 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 16/10/23 | 90 | Stores | Demand has been registered with File no 90237497 dt.26/10/2023 | Tender - Normal | 90237496 | 26-10-2023 | Proposal Approved with 90237496 dt.26-10-2023 | 90237496 | 14/12/2023 | 18/01/2024 | Tender Finalized | URBAN ENGINEERING ASSOCIATION PVT.LTD.-KOLKATA | URBAN ENGINEERING ASSOCIATION PVT.LTD.-KOLKATA | 90237496100487 | 15/03/2024 | 001 | 56468039 | LED RED Signal Aspect Main Unit 110V AC retrofittable in existing CLS Housing and compatible with AC LED ECR as per RDSO Spec:RDSO/SPN/199/2010 Revision 1.1 Firm-s offered Make/ Model: URBAN ENGINEER.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 160 | Nos. | 8932.6 | 1429216 | 13-06-2024 | 160 | 1429216 |  |  |  | 100133211001
65 | 027534 | SSE/SIG/SRM/PER, SR | NO | Sr.DSTE/II/MAS Vide No.M/SG.242/LED/RE/2023-24 dt.02.10.2023 | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00138 | 2023-10-16 | 16/10/2023 | 1 | 56468052 | LED Yellow signal Aspect main 110V AC retrofittable in existing CLS housing and compatible with AC LED, ECR/AC conventional ECR as per RDSO Spec. No. RDSO/SPN/199/2010 (Rev.1.1) | 200 | Nos. | 1770000 | 1770000 | SAG | 29333304 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 16/10/23 | 90 | Stores | Demand has been registered with File no 90237496 dt.26/10/2023 | Tender - Normal | 90237496 | 26-10-2023 | Proposal Approved with 90237496 dt.26-10-2023 | 90237496 | 14/12/2023 | 18/01/2024 | Tender Finalized | INSTAPOWER LTD-NEW DELHI | INSTAPOWER LTD-NEW DELHI | 90237496100137 | 28/01/2024 | 002 | 56468052 | LED Yellow signal Aspect main 110V AC retrofittable in existing CLS housing and compatible with AC LED, ECR/AC conventional ECR as per RDSO Spec. No. RDSO/SPN/199/2010 (Rev.1.1) Firm-s offered Make/ M.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 40 | Nos. | 8271.8 | 330872 | 28-03-2024 | 40 | 330872 |  |  |  | 100133211001
66 | 027534 | SSE/SIG/SRM/PER, SR | NO | Sr.DSTE/II/MAS Vide No.M/SG.242/LED/RE/2023-24 dt.02.10.2023 | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00138 | 2023-10-16 | 16/10/2023 | 1 | 56468052 | LED Yellow signal Aspect main 110V AC retrofittable in existing CLS housing and compatible with AC LED, ECR/AC conventional ECR as per RDSO Spec. No. RDSO/SPN/199/2010 (Rev.1.1) | 200 | Nos. | 1770000 | 1770000 | SAG | 29333304 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 16/10/23 | 90 | Stores | Demand has been registered with File no 90237496 dt.26/10/2023 | Tender - Normal | 90237496 | 26-10-2023 | Proposal Approved with 90237496 dt.26-10-2023 | 90237496 | 14/12/2023 | 18/01/2024 | Tender Finalized | URBAN ENGINEERING ASSOCIATION PVT.LTD.-KOLKATA | URBAN ENGINEERING ASSOCIATION PVT.LTD.-KOLKATA | 90237496100487 | 15/03/2024 | 002 | 56468052 | LED Yellow signal Aspect main 110V AC retrofittable in existing CLS housing and compatible with AC LED, ECR/AC conventional ECR as per RDSO Spec. No. RDSO/SPN/199/2010 (Rev.1.1) Firm-s offered Make/ M.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 160 | Nos. | 8932.6 | 1429216 | 13-06-2024 | 160 | 1429216 |  |  |  | 100133211001
67 | 027534 | SSE/SIG/SRM/PER, SR | NO | Sr.DSTE/II/MAS Vide No.M/SG.242/LED/RE/2023-24 dt.02.10.2023. | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00139 | 2023-10-07 | 07/10/2023 | 1 | 56468027 | LED Route signal lighting Unit 110V AC with built in current regulator for Railway signalling, Retrofittable in existing CLS Housing and compatible with AC LED ECR as per RDSO Specification No. RDSO/.... | 160 | Nos. | 923232 | 923232 | JAG | 29333304 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 07/10/23 | 90 | Stores | Demand has been registered with File no 90237372 dt.10/10/2023 | Tender - Normal | 90237372 | 17-10-2023 | Proposal Approved with 90237372 dt.17-10-2023 | 90237372 | 17/10/2023 | 13/11/2023 | Tender Finalized | BEACON INDUSTRIES-DEHRADUN | BEACON INDUSTRIES-DEHRADUN | 90237372101873 | 21/11/2023 | 001 | 56468027 | LED Route signal lighting Unit 110V AC with built in current regulator for Railway signalling, Retrofittable in existing CLS Housing and compatible with AC LED ECR as per RDSO Specification No. RDSO/.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 32 | Nos. | 6018 | 192576 | 19-02-2024 | 32 | 192576 |  |  |  | 100133211001
68 | 027534 | SSE/SIG/SRM/PER, SR | NO | Sr.DSTE/II/MAS Vide No.M/SG.242/LED/RE/2023-24 dt.02.10.2023. | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00139 | 2023-10-07 | 07/10/2023 | 1 | 56468027 | LED Route signal lighting Unit 110V AC with built in current regulator for Railway signalling, Retrofittable in existing CLS Housing and compatible with AC LED ECR as per RDSO Specification No. RDSO/.... | 160 | Nos. | 923232 | 923232 | JAG | 29333304 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 07/10/23 | 90 | Stores | Demand has been registered with File no 90237372 dt.10/10/2023 | Tender - Normal | 90237372 | 17-10-2023 | Proposal Approved with 90237372 dt.17-10-2023 | 90237372 | 17/10/2023 | 13/11/2023 | Tender Finalized | EFFTRONICS SYSTEMS PRIVATE LIMITED-MANGALAGIRI GUNTUR | EFFTRONICS SYSTEMS PRIVATE LIMITED-MANGALAGIRI GUNTUR | 90237372101874 | 21/11/2023 | 001 | 56468027 | LED Route signal lighting Unit 110V AC with built in current regulator for Railway signalling, Retrofittable in existing CLS Housing and compatible with AC LED ECR as per RDSO Specification No. RDSO/.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 128 | Nos. | 6065.2 | 776345.6 | 20-01-2024 | 128 | 776345.6 |  |  |  | 100133211001
69 | 027534 | SSE/SIG/SRM/PER, SR | NO | Sr.DSTE/II/MAS Vide No.M/SG.242/LED/RE/2023-24 dt.02.10.2023. | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00140 | 2023-10-07 | 07/10/2023 | 1 | 564680270980 | A- MARKER LED Signal Lighting Unit 110 Volts AC with Built in Current Regulator for Railway signaling Retrofitable in Existing CLS housing and compatible with AC LED ECR as per Specification attached..... | 35 | Nos. | 210217 | 210217 | Sr. Scale | 29333304 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 07/10/23 | 90 | Stores | Demand has been registered with File no 90237364 dt.09/10/2023 | Tender - Normal | 90237364 | 09-10-2023 | Proposal Approved with 90237364 dt.09-10-2023 | 90237364 | 02/11/2023 | 15/11/2023 | Tender Finalized | PRANAVA ELECTRONICS-CHENNAI | PRANAVA ELECTRONICS-CHENNAI | 90237364101866 | 20/11/2023 | 001 | 564680270980 | A- MARKER LED Signal Lighting Unit 110 Volts AC with Built in Current Regulator for Railway signaling Retrofitable in Existing CLS housing and compatible with AC LED ECR as per Specification attached..... | SR | 027534 | SSE/SIG/SRM/PER, SR | 35 | Nos. | 4991.4 | 174699 | 19-01-2024 | 35 | 174699 | 000944 | 22/11/2023 | SPEC | 100133211001
70 | 027534 | SSE/SIG/SRM/PER, SR | NO | Sr.DSTE/II/MAS Vide No.M/SG.242/LED/RE/2023-24 dt.02.10.2023. | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00143 | 2023-10-07 | 07/10/2023 | 1 | 430501360080 | Digital True RMS Multimeter to measure voltage 0.001-600V AC/DC, Current 0.001 to 10Amps, Frequency up to 50KHZ , Resistance up to 40M Ohms, Capacitance-.01 to 1000mfd as per GEM ID 5116877-3724984951.... | 25 | Nos. | 431550 | 431550 | Sr. Scale | 29333304 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 07/10/23 | 90 | Stores | Demand has been registered with File no 90237369 dt.10/10/2023 | GeM Coverage PO | 90237369 | 18-01-2024 | Proposal Approved with 90237369 dt.18-01-2024 |  |  |  |  | ELMACK ENGG SERVICES PRIVATE LIMITED, Chennai | ELMACK ENGG SERVICES PRIVATE LIMITED, Chennai | 90237369200086 | 19/01/2024 | 001 | 430501360080 | FLUKE Hand Held 50 KHz Digital Multimeter Brand: FLUKE (Detailed Description/Specification as per Product # 1 of GeM Contract No. GEMC-511687789589933 dt.11/01/2024) | SR | 027534 | SSE/SIG/SRM/PER, SR | 25 | Nos. | 18000 | 450000 | 26-01-2024 | 25 | 450000 |  |  |  | 100133211001
71 | 027534 | SSE/SIG/SRM/PER, SR | NO | Sr.DSTE/II/MAS Vide No.M/SG.242/LED/RE/2023-24 dt.02.10.2023. | 027534 | SSE/SIG/SRM/PER, SR | SR-027534-23-00144 | 2023-12-08 | 08/12/2023 | 1 | 570106540081 | All In One PC with 21.5 inch IPS Display, 1920x1080 pixel, minimum Intel Core I3 10100 Processor, Windows 10 pro 64 OS, Chipset Intel Q470, 3.6Ghz Base Frequency up to 4.3Ghz, 6 MB cache, 4 Cores, U.... | 5 | Nos. | 249440 | 249440 | Sr. Scale | 29333304 | SR-DIV-MAS | Demand Approved & Forwarded to Purchase Unit: - on 08/12/23 | 90 | Stores | Demand has been registered with File no 90238048 dt.15/12/2023 | GeM Coverage PO | 90238048 | 29-12-2023 | Proposal Approved with 90238048 dt.29-12-2023 |  |  |  |  | KMENTERPRISES-PUDUCHERRY | KMENTERPRISES-PUDUCHERRY | 90238048200934 | 15/05/2024 | 001 | 570106540081 | acer Intel Core i3 All in One PC with 23.8 Inch Display/ Windows 11 Professional Brand: acer (Detailed Description/Specification as per Product # 1 of GeM Contract No. GEMC-511687762663567 dt.13/03/20.... | SR | 027534 | SSE/SIG/SRM/PER, SR | 5 | Nos. | 68310 | 341550 | 30-05-2024 | 5 | 341550 | 000355 | 27/05/2024 | Delivery Period End | 100133211001